## Product Backlog- Team Euler
MoSCoW ID | Product Backlog ID | Source | Priority (M/S/C/W) | User Story ID | User Story Name | Complexity | Risk/ Impact(L-Low, M- Medium, H-High) | Type | Comments
1 | 1 |  | M | Us:101 | customer Login
2 | 2 |  | S | Us:102 | customer Registration
3 | 3 |  | C | Us:103 | customer can update profile
4 | 4 |  | W | Us:104 | login using OTP
5 | 5 |  | C | Us:105 | customer can store more than one address
6 | 6 |  |  | Us:106
7 | 7 |  |  | Us:107
8 | 8 |  |  | Us:108
9 | 9 |  |  | Us:109
10 | 10 |  |  | Us: 110
11 | 11 |  |  | Us: 111
12 | 12 |  |  | Us: 112
13 | 13 |  |  | Us: 113
14 | 14 |  |  | Us: 114
15 | 15 |  |  | Us: 115
16 | 16 |  |  | Us: 116
17 | 17 |  |  | Us: 117
18 | 18 |  |  | Us: 118
19 | 19 |  |  | Us: 119
20 | 20 |  |  | Us: 120
21 | 21 |  |  | Us: 121
22 | 22 |  |  | Us: 122
23 | 23 |  |  | Us: 123
24 | 24 |  |  | Us: 124
25 | 25 |  |  | Us: 125
26 | 26 |  |  | Us: 126
27 | 27 |  |  | Us: 127
28 | 28 |  |  | Us: 128
29 | 29 |  |  | Us: 129
30 | 30 |  |  | Us: 130

## Sprint Backlog- Team Euler
Product Backlog ID | User Story ID | User Story Task Step number | Task Step description | Assigned to | Assigned Date | Original Estimate | Adjusted estimate | Status | Actual Effort | Comment
P:01 | Us:101 | 1 | create entity class/POJO class of Customer | Roshan | 2022-08-29 | 2022-08-30 | 2022-08-31 | Done
P:02 | Us:122 | 1 | Create controller class of Customer | Akansha | 2022-08-29 | 2022-08-30 |  | In Process
P:03 | Us:104 | 1 | Create service class of Customer | Akansha | 2022-08-29 | 2022-08-30 |  | Not completed |  | Shub
P:04 | Us:124 | 1
P:05 | Us:111 | 1
P:06 | Us: 130 | 1
P:07 | Us:111 | 1
P:08 | Us:101 | 1
P:09 | Us:130 | 1
P:10 | Us:111 | 1
P:11 | Us: 122 | 1
P:12 | Us: 111 | 1
P:13 | Us:101 | 1
2
3
P:14 | Us:124 | 1
2
3
P:15 | Us:122 | 1
2
3
P:16 | Us:111 | 1
2
3
P:18 | Us:130 | 1
2
3
P:18 | Us:111 | 1
2
3
P:18 | Us:104 | 1
2
3
P:18 | Us:102 | 1
2
3
P:20 | Us:122 | 1
P:21 | Us:111 | 1
P:22 | Us:130 | 1
P:23 | Us:104 | 1
P:24 | Us:124 | 1
P:20 | Us: 102 | 1
P:21 | Us:111 | 1
P:22 | Us: 113 | 1
P:23 | Us: 105 | 1
P:24 | Us: 110 | 1
P:25 | Us:104 | 1
P:26 | Us:104 | 1
P:27 | Us:113 | 1
P:19 | Us:101 | 1
2
P:28 | Us:130 | 1
2
3
4
P:29 | Us:111 | 1
2
3
4
P:30 | Us:101 | 1
2
3
P:31 | Us:104 | 1
2
3
4
P:32 | Us:130 | 1
2
3
P:33 | Us:111 | 1
2
3
P:34 | Us:101 | 1
2
3
P:35 | Us:104 | 1
2
3
P:36 | Us:130 | 1
P:37 | Us:111 | 1
P:38 | Us:101 | 1
P:39 | Us:104 | 1
P:40 | Us:101 | 2
P:41 | Us:130 | 1
2
P:42 | Us:111 | 1
2
P:43 | Us:101 | 1
2
P:44 | Us:104 | 1
2
P:45 | Us:101 | 1
2
3
P:46 | - | 1
2
3
P:47 | Us:130 | 1
P:48 | Us:111 | 1
P:49 | Us:101 | 1
P:50 | Us:104 | 1
P:51 | Us:130 | 1
2
P:52 | Us:111 | 1
2
P:53 | Us:101 | 1
2
P:54 | 101 | 1
2
3
4